## Slide 1: Elections - The ultimate time constrained project
Marie Gregoire, PMP
Notes: Thank you
Intro – PMP 2007
Election coming up
Nothing Earth Shattering
  Fun
  PM  Important Work of Elections

## Slide 2: Elections and Project Management
A temporary endeavor undertaken to create a unique product, service, or result.
This project deadline of an Election NEVER moves
The Ultimate Time-Constrained Project

## Slide 3: It all started way back when…
General Election 1996 –
  Secretary of State’s Office - One month prior to election
  Project: Election Night Reporting over the Internet
  pro bono
Up to that point – Reporters in the next room
Solution
  Weeks prior - Access database with a user interface to enter results
  Monday prior – installed rented LAN and software
  Tuesday afternoon - trained the call-in center
  Tuesday night – summary totals web page updated by modem every 5 mins
  Wednesday - final content delivered to SOS on a “diskette”
Nebraska 1 of first 5 states to deliver reporting via Internet
Followed by ten years of consulting contracts

## Slide 4: Elections Stakeholders
Registered Voters – that’s YOU I hope!
Candidates
Political parties
Government bodies
Election Officials;
  County Election Commissioners, County Clerks
  Nebraska Secretary of State’s Office

## Slide 5: Phases of an Election
  Preparation – Initiation, Planning
    Candidate filing
    People, Polling Places, Equipment, BALLOTS
  Voting – Execution, Monitoring & Control
    Absentee voting – now called “Early Voting”
    Election Day voting at the polls
      Provisional Voting Verification Period
  Results Reporting – Certification –Close
    Election night – unofficial results
    Official results –certified by Canvass Board

## Slide 6: Scope, Time, Costs of an Election
Elections Scope– defined by law
Elections Calendar published by the AG
  “First Tuesday”
Costs; Services, ballots, equipment, poll workers, polling places
  billed back by ballot inch

## Slide 7: Risks of an Election
Election errors – lasting negative publicity, expensive corrections, destabilize public confidence
High exposure for Election Officials - Secretary of State
Change in staff at county and polls
Time window is very narrow;
  not much reaction time
  No “redo”

## Slide 8: Quality Management of Elections
Results certified by canvassing board
  Procedures set by statutes
Test ballot equipment & reporting systems
Redundant systems & processes
County Officials Training
Poll worker training; County conducted
Vendors that deliver services, ballots & equipment

## Slide 9: Communications
State and County Election Officials
  93 county teams
Candidates, Party officials
Press - 7:30 embargo, 8:00 poll close
Public – election results, candidates

## Slide 10: Issues in Elections
Vote by Mail
Voter Verifiable Paper Trail (VVPT) vs. electronic voting machines
  or Direct Recording Equipment (DRE)
  Nebraska is 100% paper
Military and Overseas voting initiatives
National Voter Registration
Internet Voting
Voter ID at the polls

## Slide 11: Election Success Indicators
No news is good news!

## Slide 12
<This page intentionally left blank>

## Slide 13: HAVA: Help America Vote Act of 2002
“Single central statewide voter registration list”
Electronic record is official record
List Maintenance
  Remove duplicates; one voter, one record
  Dept. of Motor Vehicles
  Social Security Administration
  Death Records
  Felon Records
  Movers : NCOA

## Slide 14: HAVA: Help America Vote Act of 2002
Voting equipment that is ADA compliant
Polling places that are ADA compliant
Poll Worker training
Voter Outreach

## Slide 15: Success and Risk Factors for HAVA
HAVA Requirements – Scope of Work
  Scope, Time, Cost – DOJ Penalties
  One voter, one record
  Narrow market of solution providers
  93 counties
  Tech Resources, now and future
  Fit for both large and small counties

## Slide 16: Success and Risk Factors for HAVA
Stakeholder Buy-in
  Loss of local control to the state
  Technology improvements for counties
  Build in efficiencies
  Project Representation
    large and small counties
  Continuous training

## Slide 17: Success and Risk Factors for HAVA
Quality Management
  Testing, testing, testing
  Monitor user competency
  Data and Image Conversion
    8 different legacy vendors
  Change Management
    -Roll Out – consistent repeatable process

## Slide 18: Success and Risk Factors for HAVA
Cost Controls
  Federal funds, state match
  Budget 4.2 M (10M Voter Equip)
  RFP – Fixed Price Contract
  Controlled future maintenance costs
  Who pays for what, county, state

## Slide 20: HAVA Project Phases

## Slide 21: HAVA Project Success
Met deadline January 1, 2006
First Statewide Election, May 2006 – General Election November 2006
First Statewide Petitions July 2006
Lowest cost per voter than any state

## Slide 22: A Final Public Service Message…
Doing Pro Bono work as a
Project Manager
pays dividends in many ways!
-PLEASE - Consider giving your professional skills to a worthy cause.

## Slide 23: Elections - The ultimate time constrained project
QUESTIONS?
marie@gregoireconsulting.com